## Slide 1: 500 Registrations. 7 Days. ₹2,000.
Proposed growth plan | NxtWave Growth Intern Challenge
NxtWave Growth Intern Challenge
Build Your First AI Project in 60 Minutes
500
student registrations
7
day campaign
₹2,000
total budget
Turn trusted campus networks into a measurable student acquisition engine.

## Slide 2: Start With Student Motivation
PERSONA (PLANNING HYPOTHESIS, NOT VALIDATED RESEARCH)
Final-year engineering student who wants practical AI experience but needs a clear starting point.
Goal
Build a first AI project
Barrier
Unsure where to start; worried AI needs advanced skills
Trigger
Free, beginner-friendly, 60-minute hands-on workshop
Curiosity
→
Clear first step
→
Registration
Proposed growth plan | NxtWave Growth Intern Challenge

## Slide 3: Three Channels. One Measurable System.
A. Campus ambassadors
30 ambassadors across 15 colleges
450
B. College communities
WhatsApp groups, coding clubs, placement communities
+30
C. Student creators
Tech creators and campus leaders
+20
↓
Workshop Registration + Unique Referral Tracking
500 proposed unique registrations
Targets are planning assumptions to validate. Duplicates across channels will be removed.
Proposed growth plan | NxtWave Growth Intern Challenge

## Slide 4: Launch. Measure. Optimise.
Days 1–2: Prepare
Identify 15 colleges
Recruit 30 ambassadors
Prepare referral links and assets
Days 3–4: Launch and test
Activate student communities
Test two workshop messages
Measure referral performance
Days 5–6: Optimise
Activate relevant creators
Follow up with interested students
Focus on underperforming colleges
Day 7: Close and evaluate
Final approved reminders
Verify unique registrations
Compare against the 500 target
Proposed budget allocation, subject to approval
ambassador rewards
promo support
contingency
Proposed growth plan | NxtWave Growth Intern Challenge

## Slide 5: Growth Is a System, Not a Guess
CAMPUS GROWTH TRACKER (MOCK-UP, TARGETS ONLY)
Unique registrations: 0 of 500 target
Registrations by college (15)
Ambassador leaderboard (30)
Referral-source performance (3 channels)
Three experiments
1. Ambassador referrals: registrations per ambassador
2. Message A vs. B: click-to-registration rate
3. Reminder vs. none: incremental registrations and opt-out rate
Track every source. Test every assumption. Scale what converts.
Proposed growth plan | NxtWave Growth Intern Challenge